## Sheet1
KaliMind — Autonomous Vulnerability Assessment Agent ¦ Product Backlog
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate (Days) | Actual Effort (Days)
1 | Flask Backend API Setup | MCP Server & Backend Setup | As a developer, I want a Flask REST API on Kali VM so that LLM tool calls can be executed via HTTP | Must Have | Done | The backend server starts successfully and listens on the local network interface; all tool endpoints respond with structured data; subprocess execution is managed safely throughout the tool lifecycle. | FR-01: The system shall allow the LLM to invoke penetration testing tools through the Model Context Protocol so that tool calls are executed on the Kali backend via HTTP. | Performance: each tool invocation must return results or a timeout response within a configurable time limit; partial output captured before timeout must be returned to the caller. | 3 | 3
2 | Tool Endpoint Registration | MCP Server & Backend Setup | As an LLM agent, I want 10 pentesting tools + server_health + execute_command exposed as MCP tools so that I can invoke them by name with correct parameters | Must Have | Done | Eleven tool functions are registered and available in the MCP server, covering network scanning, web enumeration, exploitation, password cracking, and general command execution, plus a health check endpoint. | FR-02: The system shall expose all penetration testing tools as named, callable MCP tool functions so that the LLM can invoke them by name with structured parameters. | Maintainability: new penetration testing tools can be registered and made available to the LLM without requiring changes to the core server or client architecture. | 2 | 2
3 | Subprocess Management | MCP Server & Backend Setup | As a backend engineer, I want isolated subprocess shells per tool call so that concurrent scans don't interfere | Must Have | Done | Each tool call runs in an isolated subprocess; output is streamed in real time from both standard output and standard error; if a tool exceeds the time limit, it is terminated gracefully with a warning before being forcibly stopped; any output captured before the timeout is returned to the caller. | FR-08: The system shall execute each tool call in an isolated subprocess shell so that concurrent tool invocations do not interfere with one another. | Reliability: subprocess execution must handle long-running processes without deadlocking or crashing the backend; graceful termination must be attempted before a forced stop is applied. | 3 | 4
4 | Nmap Integration | Reconnaissance Module | As an LLM agent, I want to run nmap scans so that I can enumerate open ports and services on the target | Must Have | Done | The network scan tool returns structured results including open ports, service names, and version information; both service detection and default script scanning modes are supported. | FR-02a: The system shall execute network port and service enumeration scans autonomously when instructed by the LLM. | Usability: the LLM shall receive structured, clearly labelled scan results that can be reasoned over directly without additional post-processing. | 2 | 2
5 | Gobuster & Dirb Integration | Reconnaissance Module | As an LLM agent, I want directory brute-forcing so that I can discover hidden endpoints on web targets | Must Have | DONE | The directory brute-force tools return a list of discovered paths; the wordlist used for enumeration can be configured per invocation. | FR-02b: The system shall perform directory and endpoint brute-forcing against web targets autonomously when instructed by the LLM. | Scalability: the architecture shall support multiple concurrent scanning sessions without degradation in output quality or reliability. | 2 | 3
6 | Result Parsing & LLM Context Feed | Reconnaissance Module | As an LLM agent, I want raw tool output fed back to my context so that I can reason over results and choose next actions | Must Have | DONE | The network scan tool returns a structured result containing standard output, error output, exit status, a success flag, a timeout flag, and any partial results captured before timeout; aggressive timing and host discovery bypass are applied by default. | FR-09: The system shall feed the complete output of every tool invocation back into the LLM context window so that the agent can reason over results and determine the next action. | Usability: tool output must be returned in a structured format that the LLM can parse and act on without manual intervention or additional formatting steps. | 2 | 3
7 | Metasploit Automation | Exploitation Engine | As an LLM agent, I want to execute Metasploit modules so that I can autonomously exploit discovered vulnerabilities | Must Have | DONE | The exploitation tool executes the selected module against the target host; it returns the session output on success or a clear error message on failure. | FR-03: The system shall execute Metasploit exploit modules autonomously against a specified target, with the module, payload, and target configuration supplied by the LLM. | Security: the exploitation engine must only be accessible from local or VPN-connected networks and must never be exposed to the public internet. | 4 | 5
8 | SQLMap Integration | Exploitation Engine | As an LLM agent, I want automated SQL injection testing so that I can detect and exploit SQLi vulnerabilities | Must Have | DONE | The SQL injection tool runs against discovered web URLs and returns a list of vulnerable parameters along with any extracted database information. | FR-04: The system shall perform automated SQL injection testing against discovered web URLs and return a list of vulnerable parameters along with any extracted database information. | Performance: SQL injection scans must complete within the configured timeout and return partial findings if the scan is interrupted before completion. | 3 | 3
9 | Payload Customization | Exploitation Engine | As an LLM agent, I want to configure exploit payloads dynamically so that I can tailor attacks to the target OS/service | Should Have | DONE | The exploitation tool accepts a payload type and target configuration; the operator can specify the remote host, local host for reverse connections, and payload type; the tool confirms the payload has been set before execution begins. | FR-03a: The system shall allow the LLM to configure exploit payloads dynamically by specifying the payload type, remote host, and local host for reverse connections before execution. | Usability: the full exploitation output including session details and post-exploitation feedback must be returned to the LLM context so the agent can chain further actions. | 4 | 4
10 | WPScan WordPress Scanner | Reconnaissance Module | As an LLM agent, I want WordPress vulnerability scanning so that I can detect plugins, themes, CVEs and weak credentials on WordPress targets | Should Have | Done | The WordPress scanning tool runs against the provided URL and returns findings including vulnerable plugins, vulnerable themes, and any discovered credentials. | FR-02c: The system shall execute WordPress vulnerability scans against target URLs autonomously, returning findings on vulnerable plugins, themes, and discovered credentials. | Usability: WPScan output must be parsed into a structured format and returned to the LLM context so that identified vulnerabilities can inform subsequent exploitation steps. | 2 | 2
11 | Nikto Web Vulnerability Scan | Reconnaissance Module | As an LLM agent, I want to run web server vulnerability audits so that I can identify misconfigurations, outdated software, and known CVEs on web targets. | Should Have | DONE | The web audit tool runs against the specified target URL and returns a list of findings including outdated server software, exposed files, insecure headers, and known CVEs; results are returned in a structured format suitable for LLM reasoning. | FR-02d: The system shall execute web server vulnerability audits against target URLs autonomously, identifying misconfigurations, outdated software versions, and known CVEs. | Usability: Nikto output must be summarised and returned to the LLM context in a structured format; full verbose output must also be available on request. | 2 | 2
12 | Hydra Brute Force Module | Cracking & Enumeration | As an LLM agent, I want brute-force attack capability so that I can test login portals for weak credentials | Should Have | DONE | The password-spraying tool supports configurable target services such as SSH, FTP, and web forms; it returns any successfully cracked credentials found during the attack. | FR-05: The system shall execute brute-force and dictionary attacks against login portals for configurable target services, returning any successfully cracked credentials. | Reliability: brute-force attacks must be subject to timeout management so that long-running attacks do not block the backend indefinitely. | 3 | 3
13 | John the Ripper Hash Cracking | Cracking & Enumeration | As an LLM agent, I want password hash cracking so that I can recover credentials from discovered hash files | Should Have | DONE | The hash-cracking tool accepts a file containing hashes and a wordlist; it returns any hashes successfully cracked within the allowed time limit. | FR-06: The system shall crack password hashes from discovered hash files using a configurable wordlist, returning successfully recovered credentials within the allowed time limit. | Maintainability: hash format detection shall be automatic where possible; the LLM shall be able to supply a custom wordlist generated from reconnaissance findings. | 2 | 2
14 | Enum4Linux SMB Scan | Cracking & Enumeration | As an LLM agent, I want to enumerate Windows and SMB environments so that I can discover network shares, user accounts, and domain information on Windows targets. | Should Have | DONE | The SMB enumeration tool runs against the target host and returns a structured list of discovered shares, local users, domain users, and password policy information; the tool completes within the configured timeout. | FR-07: The system shall enumerate Windows and SMB environments autonomously, returning discovered network shares, local and domain user accounts, and password policy information. | Usability: enumeration output must be parsed into a structured format so that the LLM can identify attack paths and credential targets for subsequent cracking or exploitation steps. | 2 | 1
15 | Tool Chaining Logic | LLM Agent Intelligence | As an LLM agent, I want autonomous tool chaining so that I can sequence reconnaissance → exploitation → cracking without human input | Must Have | DONE | The agent autonomously sequences at least three tools across reconnaissance, exploitation, and post-exploitation phases without prompting; each tool's output is passed as context into the next tool invocation; the full chain completes and produces a summary. | FR-09a: The system shall enable the LLM to invoke multiple tools in sequence across reconnaissance, exploitation, and post-exploitation phases without requiring human input between steps. | Scalability: the tool chaining architecture shall support multiple concurrent attack sessions running in parallel without interfering with one another. | 7 | 6
16 | Context-Aware Decisions | LLM Agent Intelligence | As an LLM agent, I want to adapt my strategy based on scan results so that I can avoid false positives and focus on exploitable findings | Must Have | DONE | Given scan results containing open ports and services, the agent selects the appropriate follow-up tool without human instruction; the agent correctly avoids re-running tools that have already produced valid results; decisions are logged and visible in the audit trail. | FR-09b: The system shall feed all tool output back into the LLM context window so that the agent can adapt its strategy, avoid redundant actions, and focus on exploitable findings. | Usability: tool output returned to the LLM must be complete and untruncated so that the agent has sufficient information to make accurate, context-aware decisions. | 3 | 3
17 | Automated Report Generation | LLM Agent Intelligence | As a security analyst, I want a structured vulnerability report so that I can present findings to clients without manual write-up | Must Have | DONE | After a completed assessment session, the agent produces a structured report containing an executive summary, a list of discovered vulnerabilities with severity ratings, and recommended remediation steps; the report is saved to a file in a readable format. | FR-10: The system shall generate a structured vulnerability assessment report at the conclusion of an assessment session, containing an executive summary, identified vulnerabilities with severity ratings, and recommended remediation steps. | Usability: the generated report must be readable by non-technical stakeholders and saved to a file in a portable format without requiring manual formatting. | 4 | 4
18 | API Authentication Layer | Security & Compliance | As a security engineer, I want token-based API authentication so that only authorized operators can invoke pentesting tools | Must Have | DONE | All API requests must include a valid authentication token; requests with missing or invalid tokens are rejected with an unauthorised response; the token value is configurable via an environment variable. | FR-11: The system shall restrict all API access to operators who provide a valid authentication token, rejecting unauthorised requests with an appropriate error response. | Security: the API must be accessible only from local or VPN-connected networks; internet-facing exposure must be prevented by default configuration. | 3 | 3
19 | Audit Logging | Security & Compliance | As a compliance officer, I want complete audit logs of all tool executions so that I can prove authorized use and review scan history | Should Have | DONE | Every tool invocation is recorded with the time of execution, the identity of the operator, the target, the command that was run, and a summary of the output. | FR-12: The system shall record a complete audit log entry for every tool invocation, capturing the timestamp, operator identity, target, command executed, and a summary of the output. | Maintainability: audit logs must be persisted in an append-only file format and rotated on a regular schedule to prevent unbounded growth. | 4 | 3
20 | Safe Architecture Hardening Guide | Security & Compliance | As an operator, I want deployment hardening documentation so that I don't accidentally expose the Kali backend to the internet | Should Have | DONE | The deployment guide covers setting up the virtual machine network correctly, ensuring the service is not exposed to public networks, configuring an encrypted tunnel for remote access, and applying container-based isolation. | FR-13: The system shall provide deployment hardening documentation that guides operators through securing the Kali backend, including network isolation, access restrictions, and container-based deployment options. | Portability: the backend must be deployable on a Kali Linux virtual machine, a Docker container, or bare metal without requiring architectural changes. | 3 | 4
TOTALS | [8 empty] | 53 | 55